## Before Levelling
HUSKY AIR PILOT ANGELS PROJECT - TASK LIST - BEFORE RESOURCE LEVELLING
# | TASK |  |  |  | DEPENDENCIES | RESOURCES | PM | BA | Architect | Quality Assurer | Developers | Total Effort in Hours | DURATION (Hours) | DURATION (weeks)
<------------------------------------ HOURS ---------------------------------->
1 | Husky Air Pilot Angels Project
2 |  | Management |  |  |  |  | 600 |  |  |  |  | 600
3 |  |  | Plan Project | [8 empty] | 0
4 |  |  |  | Develop Project Plan |  | PM | 40 |  |  |  |  | 40 | 40 | 1
5 |  |  |  | Update Project Plan | 4 | PM | [5 empty] | 0
6 |  | M |  | MOV and Objectives defined | 4 | [6 empty] | 0
7 |  |  | Track Project | [8 empty] | 0
8 |  |  |  | Prepare Status Reports | 4 | PM | [5 empty] | 0
9 |  |  |  | Present Status Report | [7 empty] | 0
10 |  |  | Carry out day to day Project Management |  |  | PM | [5 empty] | 0
11 |  | Analysis
12 |  |  | Gather Requirements |  | 4 | BA |  | 80 |  |  |  | 80 | 80 | 2
13 |  |  | Analyse Requirements
14 |  |  |  | Prepare logical model of the new system | 12 | BA |  | 20 |  |  |  | 20 | 20 | 0.5
15 |  |  |  | Prepare Business Model | 14 | BA |  | 20 |  |  |  | 20 | 20 | 0.5
16 |  |  |  | Prepare Data Models | 15 | BA |  | 20 |  |  |  | 20 | 20 | 0.5
17 |  |  |  | Prepare Object Models | 16 | BA |  | 20 |  |  |  | 20 | 20 | 0.5
18 |  | M |  | Analyis completed | 17
19 |  | Design | [9 empty] | 0 | 0
20 |  |  | Prepare Preliminary Design | [8 empty] | 0 | 0
21 |  |  |  | Develop Enterprise Architecture | 4 | A, BA |  | 16 | 16 |  |  | 32 | 16 | 0.4
22 |  |  |  | Prepare Dataflow Diagram | 21 | A, BA |  | 16 | 16 |  |  | 32 | 16 | 0.4
23 |  |  |  | Prepare Logical Data Model | 22 | A, BA |  | 8 | 8 |  |  | 16 | 8 | 0.2
24 |  | M |  | Logical Design Finalised | 23 | [6 empty] | 0 | 0
25 |  |  | Prepare Detailed Design | [8 empty] | 0 | 0
26 |  |  |  | Prepare Physical Model | 24 | A |  |  | 20 |  |  | 20 | 20 | 0.5
27 |  |  |  | Prepare Data Dictionary | 26 | A |  |  | 20 |  |  | 20 | 20 | 0.5
28 |  | M |  | Physical Design Finalised | 27 | [6 empty] | 0 | 0
29 |  |  | Document Design | [8 empty] | 0 | 0
30 |  |  |  | Develop Design Specification | 28 | A |  |  | 16 |  |  | 16 | 16 | 0.4
31 |  |  |  | Review Design | 30 | A, QA |  |  | 8 | 8 |  | 16 | 8 | 0.2
32 |  | M |  | Software Documentation Complete | 31 | [6 empty] | 0 | 0
33 |  |  | Design Approval | [8 empty] | 0 | 0
34 |  |  |  | Present Design to Client | 32 | PM, A |  |  | 16 |  |  | 16 | 16 | 0.4
35 |  | M |  | Client Signs off on Design | 34 | [6 empty] | 0 | 0
36 |  | Procurement | [9 empty] | 0 | 0
37 |  |  | Procure Hardware | [8 empty] | 0 | 0
38 |  |  |  | Procure Server | 35 | Pur,S | [5 empty] | 0 | 40 | 1
39 |  |  |  | Procure Workstations | 35 | Pur,WS | [5 empty] | 0 | 40 | 1
40 |  | M |  | Required Hardware Delivered | 38,39 | [6 empty] | 0 | 0
41 |  |  | Procure Software | [8 empty] | 0 | 0
42 |  |  |  | Procure Database | 35 | Pur,DB | [5 empty] | 0 | 64 | 1.6
43 |  |  |  | Procure User Interface Building Tool | 35 | Pur,UIT | [5 empty] | 0 | 80 | 2
44 |  | M |  | Required Software Tools Procured | 42,43 | [6 empty] | 0 | 0
45 |  |  | Setup and Install Hardware and Software |  | 40,44 | PM, A, V |  |  | 40 |  |  | 40 | 40 | 1
46 |  | M | Hardware and Software Installation Complete |  | 45 | [6 empty] | 0 | 0
47 |  | Development | [9 empty] | 0 | 0
48 |  |  | Develop Server Functions |  | 46 | A, D1, D2 |  |  | 80 |  | 320 | 400 | 160 | 4
49 |  |  | Develop User Interface |  | 46 | A, D3, D4 |  |  | 60 |  | 240 | 300 | 120 | 3
50 |  |  | Present Prototype to Client |  | 48,49 | A, D1, D3 |  |  | 40 |  | 80 | 120 | 40 | 1
51 |  | M | Required Software/Application Completed |  | 50 | [6 empty] | 0 | 0
52 |  | Acceptance testing | [9 empty] | 0 | 0
53 |  |  | Plan Acceptance Testing |  | 35 | PM, BA, A |  | 16 | 16 |  |  | 32 | 16 | 0.4
54 |  |  | Conduct Acceptance testing |  | 35,51 | BA, A, D1, D3, C |  | 40 | 40 |  | 80 | 160 | 40 | 1
55 |  |  | Complete Test Report |  | 54 | BA, A, D1, D3 |  | 20 | 20 |  | 40 | 80 | 20 | 0.5
56 |  | M | Test Report Completed |  | 55 | [6 empty] | 0 | 0
57 |  |  | Review Test Report and sign off |  | 56 | BA, A, C |  | 20 | 20 |  |  | 40 | 20 | 0.5
58 |  | M | Final Version of Software signed off |  | 57 | [6 empty] | 0 | 0
59 |  | Installation | [9 empty] | 0 | 0
60 |  |  | Develop Installation Plan |  | 35 | PM, A |  |  | 24 |  |  | 24 | 24 | 0.6
61 |  |  | Install at Locations |  | 57 | A, D1, D3 |  |  | 40 |  | 80 | 120 | 40 | 1
62 |  | M | Installation Complete |  | 61 | [6 empty] | 0 | 0
63 |  | Close Project | [9 empty] | 0 | 0
64 |  |  | Prepare Project Completion Report |  | 62 | PM, BA, A |  | 8 | 8 |  |  | 16 | 8 | 0.2
65 |  |  | Obtain Client sign off of Completion Report |  | 64 | PM, C | [5 empty] | 0 | 8 | 0.2
66 |  | M | Project Completion Report Signed |  | 65 | [6 empty] | 0 | 0
67 |  | Evaluate Project | [9 empty] | 0 | 0
68 |  |  | Conduct Lessons Learned Workshop |  | 62 | PM, BA, A, D1, D2, D3, D4, C |  | 16 | 16 |  | 64 | 96 | 16 | 0.4
69 |  | M | Project Closed |  | 68
[6 empty] | TOTAL | 640 | 320 | 524 | 8 | 904
[6 empty] | Rate in $ | 125 | 90 | 110 | 100 | 60
[6 empty] | Cost in $ | 80000 | 28800 | 57640 | 800 | 54240
[6 empty] | Labour | 221480
[6 empty] | Server | 6000
[6 empty] | Workstations | 4000 | $1000 each (4 workstations)
[6 empty] | Database | 7000
[6 empty] | User Interface Tool | 8000
[6 empty] | Total Budget | 246480