## Slide 1: Objectives
By the end of this session you will be able to write basic Control Plans

## Slide 2: Project Control Plans
Set up the following controls to bring the project to a successful conclusion.
Scope Management
Risk Management
Quality Management
Issue Management
Communication Management
Library

## Slide 3: Scope Change Control
Ensures that any changes to the project’s scope will help the project achieve its MOV.
Keeps the “triple constraint” in balance.
  i.e., an increase in scope will require an increase in the project’s schedule and budget.
Scope
Schedule
Budget
Text Chap. 5

## Slide 4: Scope Change Control
Mitigates:
  Scope Grope – i.e., scope poorly defined
  Scope Creep – i.e., increasing featurism
  Scope Leap – i.e., drastic change in project direction or the project’s MOV
Tools:
  Scope Change Request Form
  Scope Change Request Log

## Slide 5: Example of a Scope Change Request Form

## Slide 6: Example of a Scope Change Request Log

## Slide 7: Benefits of Scope Control
Keeps the project manager in control of the project.
  Gives the project manager the authority to manage and control the project’s schedule and budget. Otherwise she or he may ‘feel” pressured by the client or upper management to accept scope changes
Allows the project team to stay focused and on track
  Do not have to perform unnecessary work

## Slide 8: Risk Management
Text = Chapter 8.

## Slide 9
From The Project Manager’s Desk Reference – James P. Lewis
Perhaps the most famous “law” of all is Murphy’s Law, which is usually stated as “Whatever can go wrong will!”

## Slide 10
From The Project Manager’s Desk Reference – James P. Lewis
Avoid Risks – “…through better planning, not by avoiding a good opportunity.”

## Slide 11: What is Risk?
Risks are events that are beyond the project manager’s control
If not managed, risks can steer the course of activity away from the desired outcome
Risks are worth anticipating and having mitigation plans
Risk Management is the process of anticipating hurdles that might occur and putting in place a plan to mitigate the effect of these hurdles when they occur.

## Slide 12: Software Risk Management
What is Risk Management?
Why Risk Management?

## Slide 13: Three Components of Risk
Risk Impact (I)
Risk Event Probability (P)
  An estimate of the probability that a given risk event will occur
Severity of Risk Event (also called Risk Event Value) (R)
  Relationship between the components (R=P*I)

## Slide 14: Project Risk Management Processes

## Slide 15: Risk Identification
Different ways of identifying risks
  Risk identification workshops – include appropriate subject matter experts, stakeholders and outside experts
  Examining organizational history
  Using checklists and lessons learned from past projects
  Sources of risk – internal and external
  Causes and effects of risk

## Slide 16: Risk Evaluation
Determine the following
  Probability of the risk occurring
  Impact of the risk
  Risk Event Value or Risk Severity
Rank the risks based on the Risk Event Value
Identify the risks that will be managed

## Slide 17: Risk Probability
Probability is generally determined as
  High – Likely to significantly disrupt the schedule, increase cost and / or degrade performance
  Moderate – Has the potential to disrupt the schedule, increase cost and / or degrade performance
  Low – Has little potential to disrupt the schedule, increase cost and / or degrade performance

## Slide 18: Risk Impact
Impact is also determined as
  High
  Moderate
  Low

## Slide 19: Risk Severity
Risk Severity or Risk Event Value is the product of Risk Probability and Risk Impact
Low
Moderate
High
High
Moderate
High
Very High
Moderate
Low
High
High
Low
Low
Moderate
Moderate
Impact
Probability
Risk Severity
Risk Severity

## Slide 20: Risk Mitigation
Risk mitigation is a process of minimizing and/or avoiding the impact of risks
It is a set of planned actions to either prevent the risk from occurring or to minimize its impact, if it occurs
The risks that have a high expected monetary value are considered first and mitigation plans worked out

## Slide 21: Risk Monitoring
Risk monitoring is the process of continuously keeping track of the project environment and predicting the occurrence of risks
Based on some indications, mitigation actions may get triggered
Determining what indicators trigger what risks is a matter of experience

## Slide 22
Risk | Chance | Impact | Assumptions / PRECAUTIONS | Contigency
Client changes requirements | High | Changes to budget and timeline | Change Control procedures are in place | Carry out in-depth requirements analysis
Client is unsure of user interface | Medium | Changes to budget and timeline | Client will be readily available to provide feedback | 
Electrician unable to complete cabling | Low |  |  | 
Risk Management Example

## Slide 23
RISK
CHANCE
IMPACT
ASSUMPTIONS / PRECAUTIONS
CONTINGENCY
Risk Management

## Slide 24
Some words of wisdom ….
Move away from the mode of “Reactive Actions” and transform yourself to operate in the mode of “Pro-active Prevention”.

## Slide 25: Issue Management
(Not in text.)

## Slide 26
Issue and Conflict Management
Issues arise essentially due to conflicts. Therefore conflict management is the key to managing issues.
Contemporary view of conflict management
  Inevitable between human beings
  Often beneficial - produces important results, such as new ideas, better alternatives, and motivation to work harder and more collaboratively
  Natural result of change
  Can and should be managed
  Neither good nor bad, but can have positive and negative results for the organization
Project Manager must carefully select the method of managing conflict, appropriate in the organization, so that an atmosphere conducive to constructive results is developed.
Research suggests that task-related conflict often improves team performance, but emotional conflict often depresses team performance.

## Slide 27
Top Tips:
Confront the conflict head on.
Be sincere and be genuinely interested in resolving the conflict.
Listen to all the conflicting parties without any bias.
Identify areas of agreement.
Discuss areas of disagreements with an open mind and reach a Win-Win situation.
Concern for Others
High
Low
Concern for Self
Low
High
Dominating
Integrating
Obliging
Avoiding
Issue and Conflict Management

## Slide 28
Confrontation: directly face a conflict using a problem-solving approach
Compromise: use a give-and-take approach
Smoothing: de-emphasize areas of difference and emphasize areas of agreement
Forcing: the win-lose approach
Withdrawal: retreat or withdraw from an actual or potential disagreement
Collaborating: decision makers incorporate different viewpoints and insights to develop consensus and commitment
Issue and Conflict Management

## Slide 29
ISSUE MANAGEMENT
ISSUE / SITUATION
IMPACT
SOLUTIONS
RESPONSIBILITY

## Slide 30
ISSUE / SITUATION
IMPACT
SOLUTIONS
RESPONSIBILITY
ISSUE MANAGEMENT
Information gathering by email
Slow process, might miss important facts
Ask more questions, and recheck everything
PM and Client Contact
Changes to happen in a live site
Client contact not always available
Don’t know project team yet
Client has low level of IT skills.
Client staff not yet hired

## Slide 31: Quality Management
Text – Chapter 10

## Slide 32
What is Project Quality?
Conformance to requirements: the project’s processes and products meet written specifications
What is Project Quality Management?
Process of ensuring that the project’s processes and products meet written specifications
How is this ensured?
Through
Quality Planning
Quality Assurance
Quality Control
Quality Management

## Slide 33
Quality Planning
Determining the standards to be met by the project’s processes and products.
Quality Assurance
Periodically evaluating whether the standards have to be re-evaluated and re-set.
Quality Control
Performing quality control activities such as reviews, walkthrus and testing
Testing
Unit testing, System testing, Integration testing, Acceptance testing.
Black box testing, White box testing.
Quality Management

## Slide 34
ITEM
QUALITY REQUIREMENTS
QUALITY MEASUREMENT
RESPONSIBILITY
COMMENTS
TERMINOLOGY
DOCUMENTATION
REVIEW PROCESS
SIGN-OFF MECHANISM
Quality Management

## Slide 35
Item | Quality Requirements | Quality Measurement | Responsibility | Comments
Terminology | A document that defines and/or describes all terms used in documents | Prepare a glossary of terms used in the documentation (?? IT skill level ??) | Project Manager | Need to discuss with ….
Documentation | All documents should be using the same format | Prepare a standard format (template) for all documents | Project Manager | 
Review Process | All technical reports need to be checked | Hold design reviews prior to sign-off |  | 
Sign-off Mechanism | Milestones need to completed before going on to next stage |  |  | 
Quality Management Examples

## Slide 36: Communication Plan
Text – Chapter 9.

## Slide 37: Communication skills
A PM spends 90% of his/her time communicating….
And therefore this is the most important skill required for a Project Manager
The greatest threat to many projects is a failure to communicate.

## Slide 38: Project Communications Management
A subset of project management that deals with
Making the Right Information available to the Right People at the Right Time using the Right Means and Media in a Cost Effective manner.

## Slide 39: Communications Management Plan
Right People | Right Information | Right Time | Right Means | Right Media | Cost Effective Manner | By Whom | Comments
Client / Users | Project Status | Weekly | Written report; Oral presentation | Soft copy | Email and Meetings | Project Manager | Review meeting to be held each Friday 9.00 to 11.00 am
Project Sponsor | Project Status Project Financials | Weekly Monthly | Written report Financial reports | Soft copy Soft copy | Project Dashboard Financial tools Meetings | Project Manager | Financials to be reviewed monthly – 1st Monday of the month
Project Manager | Detailed Project Status | Daily Weekly | Oral reports Written reports | Soft copy | Meetings Project Dashboard | Team Leads | 
Business Analyst | User requirements | As per project schedule | Written documents with graphics, presentations, prototypes | Soft copy & software | Meetings, Email Requirements capturing tool | Users / Client | 
Architects and Designers | User requirements & design standards | As per project schedule | Written documents with graphics, presentations, prototypes | Soft copy & software | Meetings, Email Design tools | Users / Client / Business Analyst | 
Developers | Design and Programme Specifications | As per project schedule | Written documents with graphics, presentations, prototypes | Soft copy & software | Meetings, Email Specification tools | Architects / Team Leads | 

## Slide 40
COMMUNICATION MANAGEMENT
TYPE OF REPORT
WHEN
WHO TO
HOW
SPECIAL REQUIREMENTS
BY WHOM

## Slide 41
COMMUNICATION MANAGEMENT EXAMPLES
Type of report | When | Who to | How | Special Requirements | By whom | Comments
Daily update | Everyday | Client staff ?? | Phone | Ring after 7pm | Project Manager | 
Weekly review | Every Friday | Sponsor? | Meeting | Between 10am and 1pm | Project Manager | PM to invite other interested parties if appropriate
Final Review | One month after “go live” |  |  |  |  | 

## Slide 42: Project Library
Not in text.

## Slide 43
PROJECT LIBRARY
WHAT
WHEN CREATED
BY WHOM
WHEN USED
BY WHOM
LOCATION
OTHER

## Slide 44
PROJECT LIBRARY EXAMPLES
What | When created | By whom | When used | By whom | Locations | Other
Requirements | Detailed Plan | Systems Analyst | Implementation phase & Review | Project Manager | Project File in Sponsor’s office | 
Site plan | Detailed Plan | Project Manager |  |  |  | 
Network Security – Staff Access rights |  |  |  |  |  |